## Sheet1
Date Started | Task | Planned End Date | PctCompleted | ETA | Category | Comment
2021-11-01 | Tech debt: upgrade from Silverlight to HTML5 | 2022-03-31 | 10 | 2022-05-01 | Tech Debt | Delayed due to resourcing issue
2021-11-01 | Tech debt: migrate from MS SQL to MongoDB | 2022-03-31 | 15 | 2022-05-01 | Tech Debt | Delayed due to resourcing issue
2022-01-31 | Tech debt: switch to new API |  |  | 2022-03-02 | Tech Debt
2022-01-01 | Hire 2x Developers in Mumbai |  |  | 2022-02-28 | Hiring
2022-01-15 | Hire 1x Project Manager in London |  |  | 2022-03-16 | Hiring
2022-02-01 | Hire 2x Developers in Portugal |  |  | 2022-04-02 | Hiring
2021-12-24 | Bug: decimal place incorrect for INR |  | 50 | 2021-12-31 | Bug Fixes
2021-12-20 | Bug: incorrect Date format displayed |  | 100 | 2021-12-24 | Bug Fixes
2021-12-01 | New algo order |  | 75 | 2022-01-31 | New Features
2022-04-01 | Support crypto & CBDC |  |  | 2022-09-28 | New Features
2022-01-31 | Self Service Portal |  |  | 2022-04-01 | New Features
2022-03-02 | Performance improvements |  |  | 2022-05-01 | Enhancements
2022-01-01 | Ensure consistency in pricing from different servers |  |  | 2022-01-31 | Enhancements
2021-12-01 | Preprepation for Product Launch |  | 50 | 2022-01-30 | Product Launch
2022-01-30 | Product Launch: Hong Kong |  |  | 2022-02-13 | Product Launch
2022-02-13 | Product Launch: Singapore |  |  | 2022-02-27 | Product Launch
2022-02-27 | Product Launch: Thailand |  |  | 2022-03-13 | Product Launch
2022-03-13 | Product Launch: Vietnam |  |  | 2022-03-27 | Product Launch
2022-03-27 | Product Launch: Ecuador |  |  | 2022-04-10 | Product Launch
2022-04-10 | Product Launch: US |  |  | 2022-04-24 | Product Launch
2022-04-24 | Product Launch: UK |  |  | 2022-05-08 | Product Launch
2022-05-08 | Product Launch: France |  |  | 2022-05-22 | Product Launch
Formulas:
ETA = data[[#This Row],[Date Started]]+30
Date Started = [ETA, row above]