## Sheet1
Date Opened | Task | Reference Date | Reference Date 2 | Status | PctCompleted | ETA | App | Fix Component | Issue Category | Epic | Theme | Impact | Priority | Business Line | Region | Sponsor | Requestor | Assignee | Comment
2021-03-23 | NDF live streaming | 2021-05-31 | 2021-06-07 | Completed | 100 | 2021-04-30 | Client Execution | Front End | Enhancement | UX improvement | Competitive differentiation | High | Medium | FX | APAC | Ben | Ben | Sasi | Live in APAC only
2021-04-01 | Deal booking service to handle pretrade checks | 2021-09-30 | 2021-10-07 | In Progress | 50 | 2021-12-31 | Client Execution | API | Enhancement | UX improvement | Competitive differentiation | High | High | FX | Global | Ben | Raphael | Sasi
2021-06-21 | Flag deal as recurring opportunity |  |  | In Progress | 80 | 2021-09-15 | Client Execution | Back End | Enhancement | Analytics | Grow volume | Medium | Medium | FX | Global | Ben | Kenneth | Sasi
2021-07-20 | Add allocation workflow |  |  | To be prioritised | 0 |  | Client Execution | Front End | Enhancement | UX improvement | Competitive differentiation | Low | Low | FX | Global | Ben | Gaurav | Sasi
2021-04-30 | Retrocession calculation incorrect | 2021-06-30 | 2021-07-07 | Completed | 100 | 2021-06-30 | Corp Portal | API | Bug | Defects | Fix defects | High | Medium | TB | APAC | Kenneth | Chloe | Wilson
2021-06-08 | Add reporting module |  |  | In Progress | 50 | 2021-12-31 | Corp Portal | Front End | Enhancement | UX improvement | Competitive differentiation | High | Medium | TB | APAC | Kenneth | Alvin | Wilson
2021-07-05 | Add Live Chat |  |  | In Progress | 20 | 2022-03-31 | Corp Portal | Front End | Enhancement | UX improvement | Competitive differentiation | Medium | Medium | TB | APAC | Kenneth | Kenneth | Wilson
2021-08-16 | Add allocation workflow |  |  | New | 0 |  | Corp Portal | Front End | Enhancement | UX improvement | Competitive differentiation | Low | Low | TB | APAC | Kenneth | Kenneth | Wilson
2021-05-07 | Embed metrics in client screen | 2021-06-30 | 2021-07-07 | Completed | 100 | 2021-07-30 | CRM | Front End | Enhancement | Analytics | Know the clients | High | High | Transversal | Global | Joe | Dan | Simon
2021-06-10 | Add call reports |  |  | In Progress | 30 | 2022-03-31 | CRM | Back End | Enhancement | Analytics | Know the clients | Low | Low | Transversal | Global | Joe | Amrit | Simon
2021-07-12 | Alert when client consumes research |  |  | In Progress | 70 | 2021-09-30 | CRM | API | Enhancement | Analytics | Know the clients | Medium | Medium | Transversal | Global | Joe | Marc | Simon
2021-08-23 | New onboards not loaded properly |  |  | New | 0 |  | CRM | Front End | Bug | Defects | Fix defects | Low | High | Transversal | Global | Ben | Ben | Simon
2021-03-31 | Interpolation rounding error | 2021-04-30 | 2021-05-07 | Completed | 100 | 2021-04-15 | FX Margins | API | Bug | Defects | Fix defects | High | High | FX | Global | Joe | Alice | Wilson
2021-03-31 | Screen frozen when exporting data | 2021-06-30 | 2021-07-07 | In Progress | 80 | 2021-09-30 | FX Margins | Front End | Bug | Defects | Fix defects | Low | Low | FX | Global | Joe | Alice | Wilson
2021-06-24 | Self-service pricing overrides |  |  | In Progress | 75 | 2021-11-01 | FX Margins | Back End | Enhancement | Pricing | Customised pricing | High | High | FX | Global | Joe | Joe | Wilson
2021-07-27 | Pips to bps conversion for crosses incorrect |  |  | To be prioritised | 0 |  | FX Margins | API | Bug | Defects | Fix defects | Medium | Medium | FX | Global | Joe | Ben | Wilson
2021-04-07 | Client entities data not accurate | 2021-05-31 | 2021-06-07 | Completed | 100 | 2021-05-14 | Insights | API | Data Quality | Data quality | Improve data quality | Medium | Medium | FX | Global | Joe | Miranda | Wilson
2021-04-15 | "Price Discovery" mechanism for RFQ stats filter | 2021-09-30 | 2021-10-07 | In Progress | 60 | 2021-11-01 | Insights | API | Enhancement | Metrics calculations | Improve relevance | Medium | Medium | FX | Global | Joe | Hisham | Wilson
2021-06-28 | Client Sales Coverage data clean up |  |  | In Progress | 50 | 2021-11-30 | Insights | API | Data Quality | Data quality | Improve data quality | Medium | Medium | FX | Global | Joe | Farook | Wilson
2021-08-03 | NLP incorrectly classifies "total" as an entity (French energy firm) |  |  | To be prioritised | 0 |  | Insights | API | Bug | Defects | Fix defects | Low | Low | FX | Global | Joe | Ekaterina | Wilson
2021-03-01 | Performance issue with GUI | 2021-10-31 | 2021-11-07 | In Progress | 70 | 2021-12-31 | MM Offerings | Front End | Enhancement | Performance | Improve UX | Low | Low | MM | Global | Cyril | Ben | (TBC)
2021-04-14 | SSO authentication | 2021-05-31 | 2021-06-07 | Completed | 100 | 2021-05-28 | MM Offerings | API | Enhancement | Security | Improve UX | High | High | MM | Global | Cyril | Philippe | (TBC)
2021-07-02 | Add revenues data fields |  |  | In Progress | 70 | 2021-11-01 | MM Offerings | Back End | Enhancement | Analytics | Know the clients | Medium | Medium | MM | Global | Cyril | Ash | (TBC)
2021-08-09 | Flag deal as recurring opportunity |  |  | To be prioritised | 0 |  | MM Offerings | Back End | Enhancement | Analytics | Grow volume | Low | Low | MM | Global | Cyril | Kenneth | (TBC)
2021-05-10 | SSO authentication | 2021-07-31 | 2021-08-07 | Completed | 100 | 2021-08-31 | Symphony | API | Enhancement | Security | Improve UX | Medium | Medium | Transversal | Global | Cyril | Joe | Simon
2021-06-17 | SSO ID to be stored in Telemetry |  |  | In Progress | 90 | 2021-09-30 | Symphony | Back End | Enhancement | Integration | Integration with other apps | Medium | Medium | Transversal | Global | Cyril | Julien | Simon
2021-07-15 | US clients chats to be stored separately for US surveillance |  |  | In Progress | 80 | 2021-10-29 | Symphony | API | Enhancement | Compliance | Keep the lights on | Medium | Medium | Transversal | Americas | Cyril | Siobhan | Simon
2021-08-30 | Bot for FX Research & Execution |  |  | New | 0 |  | Symphony | Front End | Enhancement | Bots automation | Decrease cost of operations | Medium | Medium | Transversal | Global | Cyril | Joe | Simon