## Sheet1
Date Opened | Task | Status | PctCompleted | ETA | App | Fix Component | Issue Category | Impact | Priority | Business Line | Region | Sponsor | Requestor | Assignee | Comment
2021-03-23 | NDF live streaming | Completed | 100 | 2021-04-30 | Client Execution | Front End | Enhancement | High | Medium | FX | APAC | Ben | Ben | Sasi | Live in APAC only
2021-03-31 | Interpolation rounding error | Completed | 100 | 2021-04-15 | FX Margins | API | Bug | High | High | FX | Global | Joe | Alice | Wilson
2021-04-07 | Client entities data not accurate | Completed | 100 | 2021-05-14 | Insights | API | Data Quality | Medium | Medium | FX | Global | Joe | Miranda | Wilson
2021-04-14 | SSO authentication | Completed | 100 | 2021-05-28 | MM Offerings | API | Enhancement | High | High | MM | Global | Cyril | Philippe | (TBC)
2021-04-30 | Retrocession calculation incorrect | Completed | 100 | 2021-06-30 | Corp Portal | API | Bug | High | Medium | TB | APAC | Kenneth | Chloe | Wilson
2021-05-07 | Embed metrics in client screen | Completed | 100 | 2021-07-30 | CRM | Front End | Enhancement | High | High | Transversal | Global | Joe | Dan | Simon
2021-05-10 | SSO authentication | Completed | 100 | 2021-08-31 | Symphony | API | Enhancement | Medium | Medium | Transversal | Global | Cyril | Joe | Simon
2021-04-01 | Deal booking service to handle pretrade checks | In Progress | 50 | 2021-12-31 | Client Execution | API | Enhancement | High | High | FX | Global | Ben | Raphael | Sasi
2021-03-31 | Screen frozen when exporting data | In Progress | 80 | 2021-09-30 | FX Margins | Front End | Bug | Low | Low | FX | Global | Joe | Alice | Wilson
2021-04-15 | "Price Discovery" mechanism for RFQ stats filter | In Progress | 60 | 2021-11-01 | Insights | API | Enhancement | Medium | Medium | FX | Global | Joe | Hisham | Wilson
2021-03-01 | Performance issue with GUI | In Progress | 70 | 2021-12-31 | MM Offerings | Front End | Enhancement | Low | Low | MM | Global | Cyril | Ben | (TBC)
2021-06-08 | Add reporting module | In Progress | 50 | 2021-12-31 | Corp Portal | Front End | Enhancement | High | Medium | TB | APAC | Kenneth | Alvin | Wilson
2021-06-10 | Add call reports | In Progress | 30 | 2022-03-31 | CRM | Back End | Enhancement | Low | Low | Transversal | Global | Joe | Amrit | Simon
2021-06-17 | SSO ID to be stored in Telemetry | In Progress | 90 | 2021-09-30 | Symphony | Back End | Enhancement | Medium | Medium | Transversal | Global | Cyril | Julien | Simon
2021-06-21 | Flag deal as recurring opportunity | In Progress | 80 | 2021-09-15 | Client Execution | Back End | Enhancement | Medium | Medium | FX | Global | Ben | Kenneth | Sasi
2021-06-24 | Self-service pricing overrides | In Progress | 75 | 2021-11-01 | FX Margins | Back End | Enhancement | High | High | FX | Global | Joe | Joe | Wilson
2021-06-28 | Client Sales Coverage data clean up | In Progress | 50 | 2021-11-30 | Insights | API | Data Quality | Medium | Medium | FX | Global | Joe | Farook | Wilson
2021-07-02 | Add revenues data fields | In Progress | 70 | 2021-11-01 | MM Offerings | Back End | Enhancement | Medium | Medium | MM | Global | Cyril | Ash | (TBC)
2021-07-05 | Add Live Chat | In Progress | 20 | 2022-03-31 | Corp Portal | Front End | Enhancement | Medium | Medium | TB | APAC | Kenneth | Kenneth | Wilson
2021-07-12 | Alert when client consumes research | In Progress | 70 | 2021-09-30 | CRM | API | Enhancement | Medium | Medium | Transversal | Global | Joe | Marc | Simon
2021-07-15 | US clients chats to be stored separately for US surveillance | In Progress | 80 | 2021-10-29 | Symphony | API | Enhancement | Medium | Medium | Transversal | Americas | Cyril | Siobhan | Simon
2021-07-20 | Add allocation workflow | To be prioritised | 0 |  | Client Execution | Front End | Enhancement | Low | Low | FX | Global | Ben | Gaurav | Sasi
2021-07-27 | Pips to bps conversion for crosses incorrect | To be prioritised | 0 |  | FX Margins | API | Bug | Medium | Medium | FX | Global | Joe | Ben | Wilson
2021-08-03 | NLP incorrectly classifies "total" as an entity (French energy firm) | To be prioritised | 0 |  | Insights | API | Bug | Low | Low | FX | Global | Joe | Ekaterina | Wilson
2021-08-09 | Flag deal as recurring opportunity | To be prioritised | 0 |  | MM Offerings | Back End | Enhancement | Low | Low | MM | Global | Cyril | Kenneth | (TBC)
2021-08-16 | Add allocation workflow | New | 0 |  | Corp Portal | Front End | Enhancement | Low | Low | TB | APAC | Kenneth | Kenneth | Wilson
2021-08-23 | New onboards not loaded properly | New | 0 |  | CRM | Front End | Bug | Low | High | Transversal | Global | Ben | Ben | Simon
2021-08-30 | Bot for FX Research & Execution | New | 0 |  | Symphony | Front End | Enhancement | Medium | Medium | Transversal | Global | Cyril | Joe | Simon